LeenAI — Executive Recommendation & Master Pilot SOW (English)

Version: v1.1  •  Date: 06 Oct 2025

Executive Recommendation

**Pilot #1:** Quoter (RFQ→Quote Copilot) with a light parallel WhatsApp CX; then Café Data Platform as the second pillar.

**Why Quoter?**

- TTQ −50% with fast ROI for SMEs.

- Progressive integration (read‑only → read/write) reduces risk.

- Clear acceptance within ≤ 8 weeks; PDPL posture and guardrails in place.

**KPIs (8 weeks):** TTQ −50%, OCR ≥ 95%, ≤ 2% critical errors, ≤ 60s first pass, ≥ 20 successful RFQs.

**Team:** PM, AI Eng, Integrator, QA/UAT + (client PO/SMEs/IT).

**Timeline:** W1–2 Discovery → W3–4 Build → W5–6 UAT/HITL → W7–8 Handover & Case V1.

Unified Statement of Work — LeenAI Master Pilot SOW

**Version:** v1.1  •  **Date:** 06 Oct 2025

Introduction

This is the standard template for LeenAI pilot projects (Pilot Studio). It is PDPL‑aware and designed

to prove value quickly with clear, measurable acceptance criteria.

1) Scope (In / Out)

**In:**

- Primary use‑case: Quoter (RFQ→Quote), WhatsApp/Omni CX, Café Data Platform, or Warehouse Vision.

- Read‑only integrations first (Email/Excel/SharePoint/ERP‑API), then progressive Read/Write after acceptance.

- PromptOps & Guardrails: JSON outputs, Arabic templates, Relevance/Safety/PII filters, HITL, Evals.

- Security/Governance/PDPL: RBAC, encryption at rest/in‑transit, audit logs, DPIA, On‑prem/VPC option.

**Out:**

- Replacing ERP/CRM or full re‑engineering, enterprise data‑warehouse programs (separate contract).

2) Objectives & Expected Outcomes

- Demonstrate value within ≤ 8 weeks per pilot.

- Internal Case Study (V1) suitable for marketing.

- Reusable learnings (templates/prompts/extraction rules) for subsequent pilots.

3) Deliverables (per use‑case)

**Quoter (RFQ→Quote):**

- Working agent, OCR/Extraction, catalog/price mapping, Quote Draft (PDF/Email), TTQ/quality dashboard, runbook, training.

**WhatsApp/Omni CX:**

- 50–100 UAT scenarios, WhatsApp API integration, escalation rules, FCR/AHT/CSAT/Latency reports, content/PII guardrails.

**Café Data Platform:**

- Mini‑Lake, curated tables, internal RAG, daily exec dashboards, quality/retention policies, Q&A assistant, training.

**Vision (Warehouse/Safety):**

- Counting/congestion/safety models, calibration plan, compliance reports, Precision/Recall/FAR dashboard.

4) Timeline (6–8 weeks) & Control Gates

- Discovery (W1–2): requirements workshop, data sources, KPIs, data intake, small PoC.

- Build (W3–4): connectors/models/dashboards, Mid‑Gate.

- UAT (W5–6): acceptance scenarios, HITL, guardrails tuning, KPI measurement.

- Handover (W7–8): training, operations docs, Case Study V1, Go‑Live Light proposal.

5) KPIs & Acceptance

- Quoter: TTQ −50%, OCR ≥ 95%, ≤ 2% critical errors, ≤ 60s first pass, ≥ 20 successful RFQs.

- WhatsApp CX: FCR ≥ 60%, AHT − 25%, CSAT ≥ 4/5, Latency ≤ 2s, 50–100 UAT scenarios.

- Café: Coverage ≥ 90%, RAG ≤ 5s, MAPE ≤ 20%, 30 successful questions, two sites without Sev‑1.

- Vision: Precision/Recall ≥ 0.9, FAR ≤ 10%, 1000‑frame tests.

- PromptOps/Guardrails: Hallucination ≤ 5%, Consistency ≥ 90%, Review ≤ 24h.

6) Technical Method (practical)

- Agent + Tools: single agent with tools, optional manager pattern for specialized sub‑agents.

- PromptOps: Arabic templates, structured JSON, CoT/ReAct when needed, sampling controls (temp/top‑p/top‑k).

- Multi‑layer guardrails: relevance/safety/PII + regex/blacklists + moderation + HITL.

- Evals: golden set + accuracy/lag/consistency + weekly dashboard.

7) Security/Governance/PDPL

- Privacy‑by‑Design: data minimization, PII masking, encryption, RBAC, audit logs, retention/deletion policies, DPIA before prod,

and on‑prem/VPC option (data residency).

8) Integration Map (model)

Sources (Email/ERP/Excel/SharePoint/CCTV) → Staging → Mini‑Lake/Lakehouse → Features + LLM/RAG/Agents → APIs & Dashboards

9) RACI (brief)

- LeenAI: PM (SOW/acceptance), AI Eng (models/guardrails), Integrator (connectors/dashboards), QA (UAT).

- Client: PO, SMEs, IT/Security.

10) Pricing (Bands)

- Mini‑Pilot: 20–30k SAR (2–3 weeks) — single objective, read‑only.

- Full‑Pilot: 60–80k SAR (6–8 weeks) — integrations/governance/training.

- Support: 6–15k SAR per month — maintenance/continuous improvement.

**Payment terms (suggested):** 40% on signing, 40% post Mid‑Gate, 20% on final acceptance.

11) Client Dependencies

- Provide RFQ/files samples, read‑access credentials, PO/SMEs, IT/Security, test window.

12) Risks & Mitigations

- RFQ quality variance → HITL + multiple templates + quick training.

- LLM drift/hallucination → guardrails + evals + golden set + sampling controls.

- PDPL/data residency → on‑prem/VPC + DPIA + RBAC + encryption + minimization.

- Change resistance → enablement workshop + quick wins + runbook.

90-Day Launch Roadmap (Table Summary)

| Period | Phase | Activity | Output | Owner |
| --- | --- | --- | --- | --- |
| 06–12 Oct 2025 | Discovery | Select distributor client #1; NDA; requirements workshop; define 20 RFQs; dataset plan | Signed SOW + Kickoff | PM + Client PO |
| 13–19 Oct 2025 | Discovery | Read-only connectors (Email/Excel/SharePoint); PoC OCR/Extraction | Demo OCR V0 | AI Eng + Integrator |
| 20–26 Oct 2025 | Build | Catalog/price mapping; Quote Draft; TTQ dashboard | Demo V1 | AI Eng |
| 27 Oct–02 Nov 2025 | Build | Mid‑Gate: results review; scope lock‑in; fix‑list | Gate Report | PM + Client |
| 03–09 Nov 2025 | UAT | UAT on 10 RFQs; KPIs measurement; guardrails tuning | UAT Report V1 | QA + Client SMEs |
| 10–16 Nov 2025 | UAT | UAT on 10 additional RFQs; acceptance stabilization | Acceptance Sign‑off | PM + Client |
| 17–23 Nov 2025 | Handover | Operator training; one‑week pilot run | Runbook + Training | PM + Ops |
| 24–30 Nov 2025 | Case/Next | Case Study V1 + Go‑Live Light proposal; open WhatsApp CX Mini | Proposal + Case V1 | PM + Sales |
| 01–14 Dec 2025 | Scale | Pilot #2 (WhatsApp Mini) — 50–100 scenarios; FCR/AHT/CSAT | Pilot #2 Kickoff | GM + PM |
| 15–28 Dec 2025 | Data | Set up Café Mini (read‑only); RAG questions; daily dashboards | Café Mini Demo | Data Eng + PM |

Assumptions & Inputs used

- Based on the LeenAI zipped pack and business plan.

- KPIs/Acceptance/RACI/PDPL/PromptOps as defined in the pack.

- Commercial bands per Mini/Full/Support pricing.